1.4  California Credential Registry

◎ Foundational Year

Activity 1: AI-Enhanced CPL Infrastructure  |  Goal 2; Goal 3  |  October 11, 2026

| Status | Foundational Year |
| --- | --- |
| Progress | 15% |
| Lead | Terence Nelson |
| Budget | Included in 1.2 (CPL Credential Registry - WestEd (V0719)) |
| KPI Current | 0 Cumulative credentials published |
| 2030 Goal | 250 |
| 2030 Stretch | 900 |
| 25-26 | 0/0 |
| 26-27 | 0/50 |
| 27-28 | 0/110 |
| 28-29 | 0/175 |
| 29-30 | 0/250 |

## Description

CPL-qualified credentials are hosted on the credential registry.

## Latest Update

Date: 2026-06-29

MAP participated in a multi-stakeholder planning session with the Chancellor's Office, LWDA, WestEd, Cradle to Career, and Career Passport to align on the California Credential Registry vision and approach. The group clarified that the Credential Registry will serve as statewide infrastructure for comprehensive credential information, while Career Passport will function as the learner- and employer-facing application, with LWDA leading initial development in coordination with MAP. Next steps include developing shared technical requirements, aligning registry features across related tools, and establishing a governance structure.

## Workplan Notes

No credentials published in registry this period. Full launch not targeted until 2026-27. Standardized credential data schema incorporating TOP and CIP codes is in preparation for the registry pipeline.

## Milestones

2026: Standardized credential data schema with TOP/CIP codes; 2026-27: Registry launch

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | No credentials published yet; full launch not targeted until 2026-27; schema development underway |
| 2026-04-07 | Workplan | No credentials published in registry this period. Full launch not targeted until 2026-27. Standardized credential data schema incorporating TOP and CIP codes is in preparation for the registry pipeline. |
| 2026-03-20 | Progress Update | No credentials published yet; full launch not targeted until 2026-27; schema development underway |