3.4  Student Impact Rate Survey

○ Not Started

Activity 3: Scale CPL Access, Awards, and Procedures  |  Goal 2  |  October 26, 2026

| Status | Not Started |
| --- | --- |
| Progress | 5% |
| Lead | Terence Nelson |
| Budget | Included in 1.1 (MAP Team Operations (GFA0164)) |
| KPI Current | N/A |
| 2030 Goal | 0.9 |
| 2030 Stretch | 0.9 |
| 25-26 | —/0.7 |
| 26-27 | —/0.8 |
| 27-28 | —/0.8 |
| 28-29 | —/0.8 |
| 29-30 | —/0.9 |

## Description

Deploy CPL student impact survey tool within Student Portal to measure career and educational outcomes

## Latest Update

Date: 2026-10-15

The formal Student Impact Rate Survey has not yet launched. However, the Student Portal infrastructure needed to identify participants, capture CPL activity, and support future survey distribution has advanced significantly. Parallel student-story collection has exceeded its initial goal, but the survey instrument, automated triggers, and reporting workflow still need to be designed and deployed. With the student portal now live, this work can begin.

## Workplan Notes

Survey tool is not yet deployed. Data collection infrastructure is still under development. The CPL Student Portal launching April 2026 will include the embedded student impact survey for first-ever systematic collection.

## Milestones

April 2026: Survey tool embedded in Student Portal launch

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | Survey tool not yet deployed; infrastructure under development; will launch with Student Portal |
| 2026-04-07 | Workplan | Survey tool is not yet deployed. Data collection infrastructure is still under development. The CPL Student Portal launching April 2026 will include the embedded student impact survey for first-ever systematic collection. |
| 2026-03-20 | Progress Update | Survey tool not yet deployed; infrastructure under development; will launch with Student Portal |