1.1.3  WestEd CPL Scope of Work

↑ In Progress

Activity 1: AI-Enhanced CPL Infrastructure  |  Goal 2; Goal 3  |  October 28, 2026

| Status | In Progress |
| --- | --- |
| Progress | 40% |
| Lead | WestEd (Erin, Kathy, Rajinder) |
| Budget | Included in 1.2 (CPL Credential Registry - WestEd (V0719)) |
| KPI Current | 6 workstreams active |
| 2030 Goal | 0 |
| 2030 Stretch | 0 |
| 25-26 | 6/4 |
| 26-27 | 6/4 |
| 27-28 | 6/0 |
| 28-29 | 6/0 |
| 29-30 | 6/0 |

## Description

Skills taxonomy, credential cataloguing, NFN pilot, student experience mapping, system design, and credential registry expansion planning

## Latest Update

Date: 2026-10-15

Phase 1 is complete, and follow-on work has advanced into Credential Registry technical design, governance, user-centered design, and workforce and apprenticeship data integration. Contracting and coordination are progressing among WestEd, the Chancellor's Office, Labor Agency, Credential Engine, Career Passport, and MAP, with current focus on clarifying roles, data requirements, governance, and initial registry experience.

## Workplan Notes

WestEd CPL Scope of Work: 6 workstreams active (Credential ID, Course Alignment, NFN Use Case, Student Experience, System Design, Strategic Planning). Skills taxonomy/CTDL work progressing.

## Milestones

6 workstreams: Credential ID, Course Alignment, NFN Use Case, Student Experience, System Design, Strategic Planning