3.2  CPL Units Transcription

✔ Goal Met  ★ Stretch Met

Activity 3: Scale CPL Access, Awards, and Procedures  |  Goal 2  |  October 15, 2026

| Status | Stretch Met |
| --- | --- |
| Progress | 80% |
| Lead | Samuel Lee / Crystal Nasio |
| Budget | Included in operations (CPL Operations (ongoing $5M)) |
| KPI Current | 96,449 transcripted CPL units |
| 2030 Goal | 750,000 |
| 2030 Stretch | 930,000 |
| 25-26 | 96,449/90,000 |
| 26-27 | 96,449/195,000 |
| 27-28 | 96,449/315,000 |
| 28-29 | 96,449/450,000 |
| 29-30 | 96,449/750,000 |

## Description

Ensure CPL units are accurately reflected on student records

## Latest Update

Date: 2026-06-30

More than 100,000 CPL units have been transcripted statewide, exceeding the 2025–26 cumulative target. Growth is driven by expanded institutional participation, improved transcription practices, statewide technical assistance, faculty and counselor training, and implementation support through the MAP Initiative. Progress continues toward the 2030 goal of 750,000 transcripted CPL units.

## Workplan Notes

96,449 transcripted CPL units recorded. Exceeds the 2025-26 annual target of 85,000. Includes military (12,000), non-military (82,000), and apprentice (6,000) units.

## Milestones

2025-26 target: 85,000 (exceeded at 96,449); training on transcription procedures ongoing

## Update Log

5 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-08 | Progress Update | Cumulative transcripted CPL units exceeds 2025-26 annual target of 85,000 |
| 2026-04-08 | Workplan | 96,449 transcripted CPL units recorded. Exceeds the 2025-26 annual target of 85,000. Includes military (12,000), non-military (82,000), and apprentice (6,000) units. |
| 2026-04-07 | Progress Update | 96,449 transcripted CPL units; exceeds 2025-26 annual target of 85,000 |
| 2026-04-07 | Workplan | 96,449 transcripted CPL units recorded. Exceeds the 2025-26 annual target of 85,000. Includes military (12,000), non-military (82,000), and apprentice (6,000) units. |
| 2026-03-20 | Progress Update | 96,449 transcripted CPL units; exceeds 2025-26 annual target of 85,000 |