4.6  Sustainable Funding

↑ In Progress

Activity 4: Sprints, Projects & Partnerships  |  Goal 3  |  October 12, 2026

| Status | In Progress |
| --- | --- |
| Progress | 40% |
| Lead | Samuel Lee / James Todd |
| Budget | $89,000,000 (5-yr plan) (All CPL funding sources) |
| KPI Current | 3 distributed to colleges ($) |
| 2030 Goal | 6 |
| 2030 Stretch | 10 |
| 25-26 | 3/1 |
| 26-27 | 3/3 |
| 27-28 | 3/4 |
| 28-29 | 3/5 |
| 29-30 | 3/6 |

## Description

Advance improvements in sustainable funding models and development of external funding to support ongoing CPL work.

## Latest Update

Date: 2026-07-23

SB 135 and AB 135 were enacted, providing $7 million in ongoing funding for CPL Initiative operations, technical assistance, faculty workgroups, technology development, partnerships, and intersegmental collaboration, plus $35 million to support college awards based on CPL outcomes, projects, and innovations. The Chancellor's Office has drafted a two-year college funding model, with finalization expected in August 2026, field deployment in October 2026, and first disbursements planned for November or December 2026. Link to bills: https://legiscan.com/CA/text/AB135/id/3044016

## Workplan Notes

$50,000 distributed to 114 of 115 credit colleges and 4 noncredit campuses for CPL implementation. $6M one-time fully allocated. 2026 advocacy active for $2M ongoing + $35M one-time appropriation.

## Milestones

2026-27: $24.7M budgeted (if proposed funds approved); 2029-30: $9.1M; Total: $89M