2.3  Common Course Crosswalks

↑ In Progress

Activity 2: Faculty Workgroups & Credit Recommendations  |  Goal 1  |  October 31, 2026

| Status | In Progress |
| --- | --- |
| Progress | 30% |
| Lead | Terence Nelson |
| Budget | $200,000 (AI Skills to Course Alignment (V0515)) |
| KPI Current | 0 Cumulative validated crosswalks created |
| 2030 Goal | 200 |
| 2030 Stretch | 280 |
| 25-26 | 0/20 |
| 26-27 | 0/50 |
| 27-28 | 0/90 |
| 28-29 | 0/140 |
| 29-30 | 0/200 |

## Description

Develop AI-enabled faculty-validated CPL common course crosswalks.

## Latest Update

Date: 2026-10-18

Since May 2026, significant progress has been made on CCR assembly and curation, with S. Lee leading AI-based tool development including SkyView, an interactive systemwide instructional data viewer that may serve as the future platform for consolidating currently disconnected instructional data.

## Workplan Notes

No validated crosswalks completed yet. Development underway via three parallel approaches (Electrical, Carpentry Apprenticeship, and AI-assisted). Dependent on MAP Exhibit module releasing April 2026.

## Milestones

April 2026: MAP Exhibit module (dependency); June 2026: 20+ validated crosswalks

## Update Log

5 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-08 | Progress Update | Common Course Crosswalk functionality is built into the next release of the revised MAP Exhibit module April release |
| 2026-04-08 | Workplan | No validated crosswalks completed yet. Development underway via three parallel approaches (Electrical, Carpentry Apprenticeship, and AI-assisted). Dependent on MAP Exhibit module releasing April 2026. |
| 2026-04-07 | Progress Update | Three parallel development approaches underway (Electrical, Carpentry, AI-assisted); dependent on MAP Exhibit module April release |
| 2026-04-07 | Workplan | No validated crosswalks completed yet. Development underway via three parallel approaches (Electrical, Carpentry Apprenticeship, and AI-assisted). Dependent on MAP Exhibit module releasing April 2026. |
| 2026-03-20 | Progress Update | Three parallel development approaches underway (Electrical, Carpentry, AI-assisted); dependent on MAP Exhibit module April release |