4.4.1  VRC CPL Module Revision

↑ In Progress

Activity 4: Sprints, Projects & Partnerships  |  Goal 3  |  October 19, 2026

| Status | In Progress |
| --- | --- |
| Progress | 45% |
| Lead | Beth Kay / Crystal Nasio |
| Budget | Included in 4.3 (CCC Foundation Regional Trainings) |
| KPI Current | N/A |
| How it is counted | Each training module in production is counted |
| 2030 Goal | 4 |
| 2030 Stretch | 8 |
| 25-26 | —/0 |
| 26-27 | —/6 |
| 27-28 | —/4 |
| 28-29 | —/4 |
| 29-30 | —/4 |

## Description

Vision Resource Center technical assistance modules focused on CPL policy, procedure, resources, tools, integrations, opportunities for all constituents.

## Latest Update

Date: 2026-10-15

Continued progress on CPL Vision Resource Center module revision: 10 of 14 modules (71%) are finalized, with 8 submitted to VRC, 2 awaiting handoff, and 4 in development or review. Current focus is on completing remaining reviews, incorporating subject matter expert feedback, and submitting outstanding modules.

## Workplan Notes

VRC CPL Module revision: Review and gap analysis complete. Content development phase underway. Final packaging targeted May-June 2026.

## Milestones

Feb-Apr 2026: Content development; May-Jun: Revisions and final packaging