5.4  RP Group CPL Field Survey

✔ Goal Met

Activity 3: CPL Data Infrastructure  |  Goal 2  |  July 19, 2026

| Status | Goal Met |
| --- | --- |
| Progress | 100% |
| Lead | RP Group |
| Budget | $57,275 (RP Group Field CPL Survey (V0639)) |
| KPI Current | 1 survey completed |
| 2030 Goal | N/A |
| 2030 Stretch | N/A |
| 25-26 | 1/— |
| 26-27 | 1/— |
| 27-28 | 1/— |
| 28-29 | 1/— |
| 29-30 | 1/— |

## Description

Systemwide CPL implementation survey across all California community colleges

## Latest Update

Date: 2026-07-02

The RP Group CPL Field Survey will employ a mixed-methods research study combining quantitative analysis of student outcomes with qualitative data from institutional interviews, focus groups, and/or student surveys to examine how Credit for Prior Learning influences student success and institutional effectiveness across participating California Community Colleges. The study will analyze CPL's impact on certificate and degree completion, compare outcomes between CPL recipients and non-CPL students with attention to historically underserved populations, and assess institutional implementation practices to provide evidence-based recommendations for strengthening statewide CPL implementation and promoting equitable student success.

## Workplan Notes

Systemwide CPL implementation survey completed 2025. Results informing implementation strategy and targeted assistance.

## Milestones

Completed 2025

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | Survey completed; results informing implementation strategy and targeted assistance |
| 2026-04-07 | Workplan | Systemwide CPL implementation survey completed 2025. Results informing implementation strategy and targeted assistance. |
| 2025-06-30 | Progress Update | Survey completed; results informing implementation strategy and targeted assistance |