5.5  VRC CPL Module Revision

↑ In Progress

Activity 4: Sprints, Projects & Partnerships  |  Goal 3  |  July 13, 2026

| Status | In Progress |
| --- | --- |
| Progress | 45% |
| Lead | Beth Kay / Crystal Nasio |
| Budget | Included in 4.3 (CCC Foundation Regional Trainings) |
| KPI Current | N/A |
| 2030 Goal | N/A |
| 2030 Stretch | N/A |
| 25-26 | —/— |
| 26-27 | —/— |
| 27-28 | —/— |
| 28-29 | —/— |
| 29-30 | —/— |

## Description

Rewrite and expand Virtual Resource Center CPL training modules with CCCF/Success Center

## Latest Update

Date: 2026-07-02

Continued coordination with CCCF/Success Center on the CPL VRC module revision project, with two core modules (CPL 101/Introductory Module and CPL Leads/Coordinators) finalized and handed off to the Vision Resource Center. Several audience-specific modules (faculty, counseling, articulation, classified professionals, curriculum, apprenticeship, veterans, administrators, and MAP platform training) are progressing through review, with current work focused on incorporating reviewer feedback, coordinating subject matter expert input, and advancing remaining modules through group and secondary review toward finalization.

## Workplan Notes

VRC CPL Module revision: Review and gap analysis complete. Content development phase underway. Final packaging targeted May-June 2026.

## Milestones

Feb-Apr 2026: Content development; May-Jun: Revisions and final packaging

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | Review and gap analysis complete; content development phase underway |
| 2026-04-07 | Workplan | VRC CPL Module revision: Review and gap analysis complete. Content development phase underway. Final packaging targeted May-June 2026. |
| 2026-03-25 | Progress Update | Review and gap analysis complete; content development phase underway |