2.2  Faculty Discipline Workgroups

✔ On Track

Activity 2: Faculty Workgroups & Credit Recommendations  |  Goal 1  |  October 18, 2026

| Status | On Track |
| --- | --- |
| Progress | 44% |
| Lead | ASCCC / Calvin Klein Gloria |
| Budget | Included in 2.1 (ASCCC Pathways to Credit (V0718)) |
| KPI Current | 11 Cumulative discipline faculty workgroups active |
| 2030 Goal | 25 |
| 2030 Stretch | 36 |
| 25-26 | 11/6 |
| 26-27 | 11/15 |
| 27-28 | 11/19 |
| 28-29 | 11/22 |
| 29-30 | 11/25 |

## Description

Faculty and industry workgroups are convened to make statewide credit recommendations.

## Latest Update

Date: 2026-06-30

As of June 30, 2026, 11 faculty workgroups have completed their work which is ahead of target pace. If one splits out EMT and Wildland, as those two academic disciplines do have distinct TOPS codes from Fire Technology, we would total 13 faculty workgroups. In July 2026, we will begin meeting with HVAC faculty yet the ASCCC holds a contract to begin convening faculty workgroups to produce CPL recommendations. We are well on our way to meet the goal of 15 by June 2027.

## Workplan Notes

11 of 25 target statewide faculty workgroups convened, recommending CPL for credentials and military training across high-demand disciplines. 40 disciplines planned by 2030.

## Milestones

2025-26: 11 of 25 workgroups active; June 2026: Additional disciplines onboarded

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | 11 workgroups convened spanning high-demand fields; 101 credential exhibits documented |
| 2026-04-07 | Workplan | 11 of 25 target statewide faculty workgroups convened, recommending CPL for credentials and military training across high-demand disciplines. 40 disciplines planned by 2030. |
| 2026-03-20 | Progress Update | 11 workgroups convened spanning high-demand fields; 101 credential exhibits documented |