2.1  Statewide Credit Recommendations

✔ On Track

Activity 2: Faculty Workgroups & Credit Recommendations  |  Goal 1  |  October 16, 2026

| Status | On Track |
| --- | --- |
| Progress | 58% |
| Lead | ASCCC / Calvin Klein Gloria |
| Budget | $1,563,900 (ASCCC Pathways to Credit (V0718)) |
| KPI Current | 288 Cumulative credit recommendations |
| 2030 Goal | 1,000 |
| 2030 Stretch | 2,200 |
| 25-26 | 288/200 |
| 26-27 | 288/400 |
| 27-28 | 288/600 |
| 28-29 | 288/800 |
| 29-30 | 288/1,000 |

## Description

Create and adopt statewide CPL credit recommendations through ASCCC faculty workgroups.

## Latest Update

Date: 2026-06-30

As of June 30, 2026, we have exceeded the goal of 200 CRs from our faculty workgroups. Due to the nature of certain academic disciplines, some groups will have a very high number of CRs on exhibits while others may have single CRs to an IC or ACE CR. With that said, with a total of 288 CRs currently, we can safety state that we are well on our way to achieve the 2026/27 goal of 400 CRs within the next 12 months.

## Workplan Notes

288 cumulative statewide credit recommendations with 281 adopted this academic year. 230 currently in progress through college review and adoption workflows. Spanning military, apprenticeship, industry certification, and professional licensure fields.

## Milestones

June 2026: 650+ cumulative adopted recommendations; 2030: 1,000 target

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | 288 cumulative credit recommendations; 281 adopted this year; 230 in progress through adoption workflow |
| 2026-04-07 | Workplan | 288 cumulative statewide credit recommendations with 281 adopted this academic year. 230 currently in progress through college review and adoption workflows. Spanning military, apprenticeship, industry certification, and professional licensure fields. |
| 2026-03-20 | Progress Update | 288 cumulative credit recommendations; 281 adopted this year; 230 in progress through adoption workflow |