4.3  Strategic Partnerships

✔ Goal Met  ★ Stretch Met

Activity 4: Sprints, Projects & Partnerships  |  Goal 1  |  October 31, 2026

| Status | Stretch Met |
| --- | --- |
| Progress | 80% |
| Lead | Samuel Lee |
| Budget | Included in operations (CPL Operations (ongoing $5M)) |
| KPI Current | 20 strategic partnerships active |
| 2030 Goal | 40 |
| 2030 Stretch | 30 |
| 25-26 | 20/3 |
| 26-27 | 20/7 |
| 27-28 | 20/11 |
| 28-29 | 20/15 |
| 29-30 | 20/40 |

## Description

Build and maintain partnerships with industry, state agencies, labor unions, and education segments

## Latest Update

Date: 2026-10-14

We continue to engage with new and continuing partnerships, including LWDA on the Credential Registry, Career Passport, and projects such as EMS Corps and a potential International Rescue Committee (IRC) collaboration. A growing data share partnership with ACE is emerging, which has far-reaching potential for our service members. We are in discussions with vendors working with North Far North colleges on a portfolio approach to CPL; and we continue to deepen our relationship with the CA Dept. of Education around the Advanced CTE Framework and apprentice and pre-apprentice skills and certifications. We engaged in a follow-on contract with WestEd to continue our planning to support the forthcoming Credential Registry, which links to our ongoing contract with Credential Engine to support interoperability of CPL opportunities beyond MAP and the state. We continue to partner with the CCC Foundation on our work leveraging AI to match skills to course outcomes, and are seeing good outcomes from our contract with N2N Lightleap on AI-enabled Apprenticeship tools supporting completions, CPL awards, and outreach.

## Workplan Notes

20+ partners actively working with the CPL Initiative including DAS, CDE, ASCCC, Credential Engine, WestEd, Cal-JAC, CCCF, Futuro Health, Public Works Alliance EMS Corps, and Iron Workers union.

## Milestones

20+ partners active; expand to include Futuro Health, Iron Workers, Public Works Alliance EMS Corps

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | 25 trainings delivered incl. 6th Annual CPL Summit and 4 Regional Trainings; 1,000+ staff/faculty/admins trained |
| 2026-04-07 | Workplan | 25 trainings delivered including the 6th Annual CPL Summit and 4 CPL Regional Training Workshops. Over 1,000 staff, faculty, and administrators trained. Individual technical assistance and office hours ongoing. |
| 2026-03-20 | Progress Update | 25 trainings delivered incl. 6th Annual CPL Summit and 4 Regional Trainings; 1,000+ staff/faculty/admins trained |