4.5  Law & Regulation Review

✔ On Track

Activity 4: Sprints, Projects & Partnerships  |  Goal 3  |  October 11, 2026

| Status | On Track |
| --- | --- |
| Progress | 60% |
| Lead | Samuel Lee / James Todd |
| Budget | Included in operations (CPL Operations (ongoing $5M)) |
| KPI Current | 4 policy actions |
| 2030 Goal | 10 |
| 2030 Stretch | 18 |
| 25-26 | 4/2 |
| 26-27 | 4/5 |
| 27-28 | 4/7 |
| 28-29 | 4/9 |
| 29-30 | 4/10 |

## Description

Advance improvements to laws, regulations, procedures, and constituent resolutions focused on removing CPL barriers are enacted

## Latest Update

Date: 2026-07-02

AB 123 chaptered ($5M ongoing + $15M one-time); Title 5 updates advanced; $2M + $35M proposed in Governor's 2026 budget
AB 111 codifies new CPL funding and regulations. In 2025/26 Title 5 was updated for both CPL guidance and for the definition of a comprehensive SEP to include CPL.

## Workplan Notes

AB 123 chaptered establishing first-ever ongoing CPL state funding ($5M ongoing + $15M one-time). Title 5 regulatory updates advanced to reduce residency and access barriers. Draft trailer bill for additional $2M ongoing + $35M one-time under review.

## Milestones

2026 session: Advocate for $2M ongoing + $35M one-time; advance SCFF integration

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | $50K distributed to 114 colleges; $6M one-time fully allocated; 2026 advocacy for $2M ongoing + $35M one-time |
| 2026-04-07 | Workplan | $50,000 distributed to 114 of 115 credit colleges and 4 noncredit campuses for CPL implementation. $6M one-time fully allocated. 2026 advocacy active for $2M ongoing + $35M one-time appropriation. |
| 2026-03-20 | Progress Update | $50K distributed to 114 colleges; $6M one-time fully allocated; 2026 advocacy for $2M ongoing + $35M one-time |