4.5.1  CPL Legislative Advocacy (2026 Session)

↑ In Progress

Activity 4: Sprints, Projects & Partnerships  |  Goal 3  |  October 14, 2026

| Status | In Progress |
| --- | --- |
| Progress | 50% |
| Lead | Samuel Lee / James Todd |
| Budget | Included in operations (CPL Operations (ongoing $5M)) |
| KPI Current | N/A |
| 2030 Goal | N/A |
| 2030 Stretch | N/A |
| 25-26 | —/— |
| 26-27 | —/— |
| 27-28 | —/— |
| 28-29 | —/— |
| 29-30 | —/— |

## Description

Advocate for $2M additional ongoing + $35M one-time CPL funding in 2026 legislative session

## Latest Update

Date: 2026-07-23

SB 135 and AB 135 were enacted, providing $7 million in ongoing funding for CPL Initiative operations, technical assistance, faculty workgroups, technology development, partnerships, and intersegmental collaboration, plus $35 million to support college awards based on CPL outcomes, projects, and innovations. The Chancellor's Office has drafted a two-year college funding model, with finalization expected in August 2026, field deployment in October 2026, and first disbursements planned for November or December 2026.
Link to bills: https://legiscan.com/CA/text/AB135/id/3044016

## Workplan Notes

Governor's 2026 budget includes proposed $2M ongoing + $35M one-time. Legislative session runs through September 2026. Monitoring and providing evidence to support advancement.

## Milestones

Governor's 2026 budget includes proposed $2M ongoing + $35M one-time; legislative session through September